Save the White Lion Pailton

Invitation to Tender

For

Design Team Lead

Issue Date: 9th December 2022

Return Date: 9am, Monday 9th January 2023

CONTENTS

- Overview and Project Scope

- Scope of service

- Evaluation Criteria

- Supporting Information

- Instructions for Tenderers

Attachment 1:  Form of Tender

Attachment 2: Programme

Attachment 3: Organisation Structure

Outline Sketch Designs

# Overview and Project Scope

The White Lion is a much-loved 18th century coaching inn, at the heart of the village of Pailton, North Warwickshire. It is Listed Grade II and has been at the heart of its community for over 300 years.

Over this time, the pub continuously changed and adapted to meet local needs, but it has retained both its architectural and social significance. There are clearly legible parts of the original timber framed structure still in place, along with evidence of former stables and domestic outbuildings. The context of the site is very much a key focal point along the village’s main street (Coventry Road). The

pub is well set back from the road, with land to both the sides and rear. This established setting creates a strong visual and heritage focus for the village and its community.

The pub has, however, been closed for seven years, and is in poor repair. Its condition is fragile and deteriorating – without a plan for restoration now, this building, so important to the identity and history of the village, will be lost.

The aim of the community led project to Save the White Lion is to restore and renew the building and grounds and establish a sustainable community business at the heart of our village.

The local community mandated Pailton Parish Council (PPC) via the Pailton White Lion Working Group (PWLWG) to purchase the White Lion and since then the Working Group has carried out extensive community consultation to establish local residents’ priorities for what the White Lion needs to provide for the village and the local area. These community consultations have provided us with a very clear set of aspirations for the future of the White Lion.

In summary, the plan is that the White Lion will provide: a community shop and post office; a pub and café/restaurant, extending into the grounds to the side and rear; workspace for artisan producers and makers in the one-time stable block and in the main building during quieter times; overnight/holiday accommodation on the upper floors; outdoor space for eating out, farmers’ and makers’ markets and a wide range of community activities.

The capital development project that we have developed includes:

- Full conservation and restoration of the Listed buildings, incorporating sustainable technologies for carbon neutral operation.

- Demolition of the modern block detracting from heritage significance.

- Reuse of the ground floor to provide, licensed areas for food and drink and kitchen and possible deli

• 	Creating six en-suite rooms on the first floor and a large suite on the second floor for overnight/holiday accommodation.

- Restoring the historic stable block to provide working space and jobs for artisan producers shop and Post Office and/or local businesses.

- Landscaping external areas, providing disabled access, attractive gardens and garden loggia.

- Creating spaces and facilities for community activity, particularly for families and older generations facing isolation.

- Telling the stories of the village and its pub through interpretation and digital outputs.

A conceptual layout has been developed and is presented as Attachment 4.

The duration of the project and structure of the project plan are influenced by the Heritage Fund award process which divides the project into two stages.  Firstly, a Development Phase which encompasses RIBA Stages 1 to 3 and secondly a Delivery Phase which encompasses RIBA Stages 4 to 7.

The Project will provide a unique local opportunity for people to develop skills and learn about heritage.  We are expecting our Project Team to fully engage with this process by contributing to hard hat tours on-site by the public, key stakeholders and heritage professionals, give public talks within the community and a talk at a local school careers fair. The Project Team is not expected to organise these events, but they are expected to attend and some events may happen outside the normal working week. Any fee proposals, therefore, should include provision for this engagement, further details of which will be provided.

The contract will run from January 2023 to February 2026 (February 2027 End of Defects Liability Period) with a stand down period when the application is being assessed. Key dates for design, mobilisation and build are provided in Table 2.

Overall costs for conservation, restoration and rebuild are estimated to be in the region of £850,000 (exc. VAT)

# Scope of Service

Pailton Parish Council is seeking proposals for the provision of a range of consultancy support services for the White Lion Project and the development of the National Lottery Heritage Fund (NLHF) Stage 2 Heritage Enterprise application and the subsequent delivery of the project on site.

The Parish Council seeks to appoint a comprehensive multidisciplinary team, consisting of, but not necessarily limited to:

2.1	Architect/Design Team Leader/ CDM Principal Designer

## 2.2		Structural Engineer

2.3	Services Engineer

At the time of this appointment a Feasibility Study has been completed which has taken the project to the point where a Concept Design has been produced and agreed. Associated construction costs and Professional Fees have been estimated.

The project organisation structure has been determined and is presented in Attachment 3 and Greenwood Projects Ltd have been appointed for Project Management.

## Architect/Design Team Leader/ CDM Principal Designer

The Design Team Lead will be the Architect reporting to the PWLWG and will be responsible for all aspects of the design and statutory approvals.

This tender is for an Architect led, multidisciplinary design team of suitable qualified and experienced specialists including a Building Services Engineer, and Civil & Structural Engineer.

The Design Team will also advise on all site survey requirements and undertake the necessary procurement (requirement to obtain three quotations wherever possible) and commission their execution. The Design Team will also, with the Project Manager, procure services for any other consultancy service required in order to develop the project including (but not limited to) Fire Consultancy, Access Consultancy, Ecologist input, and Archaeological services.

It should be noted that the Design Team will stand down during the Heritage Fund Delivery Phase assessment when there will be a break clause in contract of services.  The Design Team will re-start on the condition that the Heritage Fund funding is approved and at the discretion of the Client.

General Requirements

The Design Team Lead will ensure all members of the Design Team are aware of the tasks and responsibilities attributed to them. They will maintain regular contact with all team members to ensure that any issues are identified with minimum delay and appropriate corrective action is taken where necessary.

The Architect will be responsible for identifying any surveys that are required, advising the Client’s representatives, writing the briefs and procuring them in line with Heritage Fund guidelines and overseeing them.

Responsibilities include:

- The Design Team Lead will be responsible for holding / chairing regular Design Team meetings, which will be recorded appropriately with minutes of meetings being distributed to the design team and others as appropriate.

- Act as Principal Designer under the terms of the CDM regulations.

- Prepare and monitor compliance with the Health and Safety Plan

- Produce design information against the programme, and if delayed use reasonable endeavours to expedite the production of the information.

- Provide suitable value engineering / re-scoping options as part of a coordinated value engineering exercise as required to mitigate against any uplift in projected construction and management costs.

- Provide rationale and justification for design team changes where appropriate to support the change control process employed on the project.

- Prepare/issue coordinated End RIBA Stage Design Reports and present to the Client

- Prepare applications for statutory approvals

- Provide material to support publicity for the project

- Keep full and accurate records of all key meetings and negotiations attended or conducted and make the same available to the Society’s representatives.

- Co-ordinate and submitting a monthly progress report, input into the overall project programme, cost reports and risk register.

- Agree reporting procedures and meeting schedules

RIBA Stage 1 - Preparation

  - Receive an initial brief from the Client based on the NLHF Round 1 submission covering the vision, aims and objectives of the project, business plan, project budget, outline accommodation schedule and the options considered to date. Take note of the Client’s policies for environmental sustainability, inclusive design, heritage skills training and community engagement. Include in a Project Definition Report.

1.2	Establish and chair regular meetings with the design team and others through the Preparation Stage in order to monitor progress. Circulate minutes of the meetings to the Client’s Project Manager and others. The minutes shall record the action and indicate who is responsible for taking that action.

1.3	Carry out an inspection of the site and a review of the design exploration to date, including a review of existing documentation and the stage one NLHF application. Include the following in the Project Definition Report:

• 	advice on matters relating to statutory and legal requirements;

• 	initial response to the present condition and use of the building;

• 	initial response to the sketch schemes prepared to date, with regard to the Client brief.

1.4	In consultation with the Client and design team members, prepare detailed briefs and secure competitive quotes for site surveys, investigations and materials testing, etc. Obtain records of existing services. Arrange for the carrying out of all such surveys and investigations authorised by the Client, interpret the results and, if necessary, make recommendations to the Client.

1.5	Develop the project brief, agree reporting procedures and meeting schedule and obtain existing information. Include in the Project Definition Report.

1.6	Provide material for a RIBA Stage 1 public consultation. Make amendments to the brief as agreed with the Client, in response to the outcome of public consultation activities.

1.7	Undertake risk assessments and contribute to the Project Manager’s risk management process. Include in the Project Definition Report.

1.8	Undertake value management exercises. Include in the Project Definition Report.

1.9	Submit Project Definition Report and obtain the Client approval to proceed to Stage 2.

RIBA Stages 2, 3 and 4 - Concept Design, Developed Design and Technical Design

2.1 	Chair regular meetings with the design team and others throughout these stages to monitor progress. Circulate minutes of the meetings to the Client’s representative and others. The minutes shall record the action to be taken and indicate who is responsible for taking that action.

2.2	Reaffirm the Client brief and budget in the light of the Stage 1 review.

2.3	Present the condition survey and schedule of further surveys required in a report for the Client and funders.

2.4	In co-operation with other members of the design team, develop RIBA Stage 2 Concept Design and submit to the Client including a review of programme and costs. Incorporate advice on energy conservation and energy targets.

2.5	Prepare visual information for Client, stakeholder and public consultation. Provide RIBA Stage 2 Concept Design Report and present to the Client, NLHF and other stakeholders at a RIBA Stage 2 Review meeting.

2.6	Obtain Client approval to proceed to RIBA Stage 3 Developed Design.

2.7	In co-operation with the other members of the design team, develop the scheme design within the approved cost and submit to the Client for approval, giving details of proposed specification and services.

2.8	Consult as necessary with the Planning Authority and any other statutory authority or relevant advisory body as required, on matters relating to the proposed Works.

2.9	In liaison with the other members of the design team, assist in the preparation of a cost plan based on the approved cost and the anticipated start and completion dates. Provide advice regarding options for the procurement of the Works.

2.10	Provide presentation quality drawings, exhibition boards and materials to facilitate RIBA Stage 3 Developed Design, public consultation. Attend consultation events as required by the Client and partner organisations. Incorporate outcomes as agreed with the client.

2.11	Provide RIBA Stage 3 Developed Design Report and present to the Client, and other stakeholders at a RIBA Stage 3 Review meeting.

2.12	Undertake further scheme development to meet requirements for submissions of Planning and Listed Building Consent. Prepare a detailed specification for the works of repair and conversion. Prepare a design and access statement, heritage impact assessment. Submit the Planning and Listed Building Consent applications.

2.13	Assist the Client’s Project Manager in the preparation of a ten year management and maintenance plan for the project, including preparation of costed schedules of cyclical maintenance and testing to be undertaken by volunteers, tenants /occupiers and contractors.

2.14	Prepare and present such other information as might be required to compete the NLHF and other funding applications and to respond to assessor’s queries.

2.15	Obtain Client approval to proceed to RIBA Stage 4 Technical Design subject to the approval of all funding and the confirmation of the client that the project and appointment are to proceed.

RIBA Stages 4 and 5 - Technical Design and Specialist Design

3.1	Review the NLHF stage two award grant conditions and note the approved purposes.

3.2	Establish and chair regular meetings with the design team and others in order to monitor progress and to take any action necessary to correct any deficiencies in design information.

3.3	Circulate minutes of the meetings to the Client’s Project Manager and others. The minutes shall record the action to be taken to rectify any deficiencies and shall indicate who is responsible for taking that action.

3.4	In co-operation with the design team prepare a detailed programme for the preparation of design and production information leading up to obtaining tenders for the Works. Provide a copy of the programme to the Client’s representative for Client approval.

3.5	Provide presentation quality drawings, exhibition boards and materials to facilitate RIBA Stage 4 Technical Design, public consultation. Attend consultation events as required by the Client and partner organisations. Incorporate outcomes as agreed with the client.

3.6	Provide RIBA Stage 4 Technical Design Report and present to the Client, NLHF and other stakeholders at a RIBA Stage 4 Review meeting.

3.7	Obtain Client approval to proceed to RIBA Stage 5 Specialist Design

3.8	Ensure the timely exchange of design or other information between the  members of the design team.

3.9	Establish regular reporting procedures with the Client’s representative, identifying those matters which require approval and, where necessary, provide assistance to obtain those approvals.

3.10	Make recommendations to the Client on the need for specialist consultants or contractors to design, or to design and execute, any sections of the Works or for specialist suppliers to provide any materials or equipment and obtain the Client's approval and take any action necessary to implement the Client's decision.

3.11	Co-ordinate all design work, ensure that the designs are fully integrated and are tested throughout the design phase against costs targets and planning or other controls and take any action necessary.

3.12	Ensure that the designs for the Works fully comply with all Statutory Requirements or Regulations including, but not confined to requirements concerning Health and Safety, Planning, Fire, Building Control, etc., and take any action necessary.

3.13	Make all necessary submissions to statutory authorities to satisfy Planning or Listed Building Consent conditions and to obtain approvals. Ensure that all utilities and other necessary services are in place both for the construction phase and for permanent operation following completion of the Project.

3.14	Give the Client’s representative sufficient notice of all approvals, decisions or other matters which require action by the Client and where appropriate assist the client by providing information and making recommendations.

3.15	Ensure that life cycle costings and environmental assessment techniques are applied to the design for the Project and adopt solutions giving the best overall value for money and, where this may result in the cost limit for the project being exceeded, make recommendations to the Client and obtain instructions.

3.16	Ensure that the specifications prepared for the Works specifically exclude the use of materials accepted as being deleterious at the time and subsequently ensure that such materials are not used in connection with the Works.

3.17	In co-operation with the other members of the design team, complete the design of the Project up to tender stage.

3.18	Discuss with the Client, QS and project manager the need for site inspection staff and obtain instructions.

3.19	Consider the most suitable options for the procurement of the Works. Advise on the most appropriate form of Contract to be used. Following discussion with the project manager and other members of the design team, make recommendations to the Client and obtain instructions.

3.20	Advise the client on the content and assessment criteria for the Pre-tender Qualification Questionnaire. Assist the Project Manager in the implementation of the first stage selection process.

3.21	In liaison with the other members of the design team, make recommendations to the Client on the suitability of contractors who may be invited to submit a tender for the main works and any specialist works and obtain instructions.

3.22	In liaison with the other members of the design team, ensure that all drawings, specifications, schedules, bills of quantities or other documents necessary for the placing of contracts are completed and are fully coordinated, are in accordance with the brief approved by the Client and are available on the programmed date.

3.23	Ensure that a pre-tender cost check is prepared based on the tender documentation and inform the Client of the result of that check.

3.24	Agree with the Client and their Project Manager, final arrangements for the obtaining and assessment of tenders.

3.25	Undertake risk assessments.

3.26	Undertake value management exercises.

3.27	As required in coordination with the Project Manager, arrange for tenders to be returned direct to the Client in accordance with the Client's tendering procedures.

3.28	Assist the Client’s Project Manager to deal with all enquiries from the contractors during the tendering period and ensure that any clarification on the content of the documentation given to a tenderer is copied to other firms tendering.

3.29	Copy all correspondence regarding the obtaining of tenders direct to the Client and Project Manager.

3.30	Examine tenders received and, in liaison with the Project Manager and other members of the design team, make recommendations to the Client and advise on any corrective design action which may be required if the lowest tender is higher than the approved cost for the Works and obtain the Client instructions.

3.31	Together with the Project Manager and QS ensure that any tender under consideration for acceptance has been subjected to an arithmetical and technical check and that any errors have been resolved in accordance with the Client procedure.

3.32	Obtain the Client's instructions regarding the acceptance of a tender.

3.33	Together with the Project Manager and QS obtain the Client's approval to proceed to Stage 6 Construction.

RIBA Stage 6 – Construction

4.1	If required, and as determined by the contract and construction strategy and the appointment of contractor, undertake the role of Contract Administrator.

4.2	In liaison with the other members of the design team, provide the Client with drawings or other documents necessary for entering into the contract.

4.3	Undertake risk assessments.

4.4	Undertake value management exercises.

4.5	Provide such assistance as the Client’s Project Manager may require in order that they can agree a detailed programme for the Works with the Contractor which specifies completion by the agreed date.

4.6	Attend the meetings with the Contractor or with others.

4.7	Chair regular meetings with the design team to review design information and monitor the distribution of that information to the Contractor and the other Consultants as may be necessary and circulate minutes of the meeting to the Client’s representative and to the other Consultants. The minutes shall record the action to be taken and shall indicate who is to be responsible for taking that action.

4.8	Until completion of the Project, continue reporting to the Client and Project Manager in accordance with procedures established under Stage 3.

4.9	In compliance with the selected contract form and construction method, collaborating with the other members of the design team, administer the terms of the Works contract during operations on site and relating to the completion of the Works.

4.10 	In compliance with the selected contract form and in liaison with the Client and other members of the design team, observe contract Change Control procedures. Adhere to the Client’s authorisation levels prior to issue of Architect’s Instructions.

4.11	Support the Project Manager to ensure that the QS maintains cost management procedures in order to ensure financial control and issues monthly cost reports to the Client’s representative.

4.12	Until completion of the project, report to the Client’s Project Manager at monthly intervals on the progress of the Works.

4.13	As Principal Designer ensure that rigorous safety policies are in place and are implemented by the Contractor and sub-contractors working on the site and that there is adequate protection for the public and others and that Health and Safety statutory requirements or regulations are fully observed.

4.14	Ensure that rigorous quality management procedures are in place throughout the construction phase.

4.15	Attend regular meetings with the Contractor and the other members of the design team as necessary in order to monitor the progress of the Works and the production of design information to the Contractor. Provide written reports and monitoring statements as required to satisfy the requirements of the funding bodies and support the Client’s Project Manager/QS in making interim grant claims.

4.16	Visit the site at regular intervals during the construction of the Works in order to inspect the quality of the work and to monitor progress and ensure that the Works are completed fully in accordance with the contract documents.

4.17	Assist the Client to ensure that adequate records and photographs are available at all times throughout the construction phase, to record day to day progress of the Works.

4.18	Inform the Client of any contractual difficulties which may arise during the course of the contract and obtain the Client’s instructions.

4.19	Liaise as necessary with the other members of the design team/QS and issue interim payment certificates in accordance with the terms of the construction contract.

4.20	Together with the Project Manager, inform the Client four weeks prior to the anticipated date of completion of the Works. Assist the Client through the provision of documentation to obtain appropriate insurance ahead of handover and to support any legal transactions.

4.21	Ensure that all defects are rectified. Issue Certificates relating to the practical completion of the Works.

RIBA Stage 7 - Use and Aftercare

5.1	Ensure that the Works are cleaned, tested and commissioned prior to handover to the Client.

5.2	Attend a Client handover meeting and ensure that the End User understands and accepts the building condition at practical completion. Make arrangements for monitoring and, if necessary, rectification of defects during the Defects Liability Period and ensure that the Client understands the process.

5.3	In liaison with the other members of the design team, organise and attend a Client handover briefing to ensure that all services and systems operations are demonstrated to the Client and End Users, and that all documentation requiring sign off at handover is completed.

5.4	In liaison with the other members of the design team, provide the Client with a set of record drawings and formal written guidance on the operation and maintenance of the Project and its services. Ensure that the Contractor provides all manuals and completes the Health & Safety files, in the formats required.

5.5	Issue a list of defects to the Contractor at the appropriate time in accordance with the terms of the Works contract.

5.6	Ensure that the Contractor rectifies the defects within a reasonable time and issue a Certificate to the Contractor when all defects have been made good.

5.7	Liaise with the other members of the design team and QS regarding final valuation of the Works and report the final cost of the Works to the Client.

5.8	Liaise with other members of the design team and QS and issue the Final Certificate and any other documentation required by Client in satisfying the completion requirements of the NLHF and other funders.

## Structural Engineer

- Detailed design service for the following:

- Site Investigation.

- Earthworks, excavation and ground stabilisation.

- Demolition of structures.

- Foundations (including forms of piling but not the design of proprietary piling).

- Earth and/or water retaining structures (including reinforced earth).

- Ground and surface treatment (including treatment of any underground structures eg caves.)

- Local, mains, public health and land drainage, inspection chambers, sewers, interceptors, tanks, treatment works and ground dewatering.

- Paving and surfacing, road, car parks and footpaths.

- Structures in-situ or precast concrete (employing any reinforcement or other techniques).

- Structures in masonry, brickwork or blockwork (including any reinforcement or other techniques, wall ties and structural metalwork, etc).

- Structures in steelwork and metalwork whether ferrous or non-ferrous.

- Structures in timber reinforced plastics or other materials used for structures (including forms of roof truss but not the design of proprietary roof trusses).

- Soil waste and vent pipework in conjunction with the M&E Engineer.

- Such other elements as the Consultant may consider appropriate and/or the Employer may instruct.

- The Engineer shall attend meetings and visit site to properly progress the works to ensure the successful completion of the Project and mitigate any delays or additional costs.  Meetings will include, but not be limited to, Client, Project Manager, Lead Design Consultant/Architect, Quantity Surveyor, Structural Engineer, Mechanical & Electrical Engineer, Project/ Design Team and Site Progress.

- Issue monthly Project Progress reports detailing the project status under the following headings:

Works Undertaken

Forthcoming Actions

Information / Decisions / Key Actions Required

Risk Issues

Issued Information / Design Status.

- perform the Services necessary for completion of the Design Stages in line with the project programme.

- Monitor the production of design information against the design programme and if delayed advise the Project Manager so that action can be taken accordingly.

- Liaise closely with any appointed Designers throughout and ensure coordination of the construction works.

- Input into development of the master programme and project element programmes for the project and support the team in regularly reviewing these.

- Provide cost advice on maintenance, life cycle costing and prepare cost in use studies accordingly and input into the production of the 10 Year Management and Maintenance Plan for the project.

- Assist with risk identification and reduction strategies.

- Assist with value engineering exercises to ensure alignment with budget.

- print, reproduce or purchase all documents, drawings, maps, models, photographs and other records necessary for the proper performance of the Services.

- provide information to the Project Manager, the Consultants and to the Contractors from time to time as necessary to enable them to carry out their respective duties.

- keep full and proper records of all key meetings and negotiations attended or conducted and make the same available for inspection by the Client forthwith on request.

- deliver the Project in line with the Project Execution Plan (PEP) and report progress against the PEP baseline throughout.

- Assist and provide necessary information to Lead Designer for production of HLF ‘10 Year Management and Maintenance Plan’.

- Support and monitor as appropriate applications for all permissions, approvals, consents and the like required by any statute, regulation of the like relating to the project and advise the Client accordingly.

- Comply fully with the Client’s change control procedures.

## Mechanical and Electrical Engineer

The engineering works will include all the construction and conservation works relating to the whole of the site, and the scope of services for the Engineer may include the following work elements for which the Consultant is to provide a detailed design service, if required;

##### Mechanical Work Elements

- Acoustical design and treatment of the Works (control of M and E plant noise only).

- Air conditioning and mechanical ventilation services.

- Performance and control of automatic blinds and shutters – selection of blinds and shutters by others.

- Automatic controls and energy management.

- Boiler plant and auxiliaries.

- Calorifier plants.

- Cooling water services.

- Distribution mains for all services

- Exhaust, gas, treatment and flues.

- Fire protection services.

- Fuel gas and distribution fuel plant and auxiliaries.

- Heating installations.

- Hot water services.

- Lifts, hoists and escalators.

- Mechanical air-handling plant installations.

- Noise attenuation to M and E plant.

- Statutory undertakers’ incoming supplies.

- Thermal insulation.

- Vibration control.

- Water filtration and treatment systems.

- Provision of service supplies for window cleaning and other external access equipment.

##### Electrical Work Elements

- CCTV systems.

- Earth bonding.

- Electrical distribution services.

- Electrical lighting and power installations and power installations including light fittings.

- Electrical substations and switchgear.

- Emergency lighting.

- Energy management.

- Fire detection and alarm systems.

- Floodlighting systems.

- Passive information technology systems / networks (IT strategy and hardware by others).

- Intruder detection and alarm systems.

- Lightning protection.

- Mechanical services and plant wiring.

- Security and access control systems.

- Small power distribution system.

- Statutory undertakers incoming services.

- Telephone installations and exchanges (passive network only).

##### Plumbing

- Services in connection with the sanitary ware – architect to specify the sanitary fittings.

- Hot and cold water installations and services.

- Distribution mains for all plumbing services.

- Public health and plumbing services.

- Soil waste and vent pipework in conjunction with the Structural Engineer.

- Cast iron and copper pipework relating to the soil waste and vent pipework in conjunction with the structural engineer.

General

- The Engineer shall comply with the responsibilities of a designer as defined by the Construction (Design and Management) Regulations 2015.

- attend meetings and visit site to properly progress the works to ensure the successful completion of the Project and mitigate any delays or additional costs.  Meetings will include, but not be limited to, Client, Project Manager, Lead Design Consultant/Architect, Quantity Surveyor, Structural Engineer, Mechanical & Electrical Engineer, Project/ Design Team and Site Progress.

- issue monthly Project Progress reports detailing the project status under the following headings:

Works Undertaken

Forthcoming Actions

Information / Decisions / Key Actions Required

Risk Issues

Issued Information / Design Status.

- The Engineer shall be required to liaise and work in close collaboration with the Client, Project Manager, Lead Design Consultant/Architect, Quantity Surveyor, Structural Engineer, Principal Designer and the wider professional team with the intent to maximise the project’s success.

- Perform the Services necessary for completion of the Design Stages in line with the project programme.

- monitor the production of design information against the design programme and if delayed advise the Project Manager so that action can be taken accordingly.

- liaise closely with any appointed designer throughout and ensure effective coordination of the construction works.

- input into development of the master programme and project element programmes for the project and support the team in regularly reviewing these.

- provide cost advice on maintenance, life cycle costing and prepare cost in use studies accordingly and input into the production of the 10 Year Management and Maintenance Plan for the project.

- assist with risk identification and reduction strategies.

- assist with value engineering exercises to ensure alignment with budget.

- print, reproduce or purchase all documents, drawings, maps, models, photographs and other records necessary for the proper performance of the Services.

- keep full and proper records of all key meetings and negotiations attended or conducted and make the same available for inspection by the Client forthwith on request.

- deliver the Project in line with the Project Execution Plan (PEP) and report progress against the PEP baseline throughout.

- perform such other duties as may reasonably be required by the Client to ensure the completion of the Project.

- support the Client and the Project Manager in any negotiations required with wider stakeholders and others as appropriate including the production of drawings to support legal documentation.

- Assist and provide necessary information to Lead Designer for production of HLF ‘10 Year Management and Maintenance Plan’.

- support and monitor as appropriate applications for all permissions, approvals, consents and the like required by any statute, regulation of the like relating to the project and advise the Client accordingly.

## 3	Tender Requirements & Assessment Criteria

## Timetable

## Deadline

Completed tenders should be returned by email by Monday 9th January 9am.

No questions will be accepted after midday on Wednesday 4th January 2023.

It is the Tenderer’s responsibility to ensure that they are received on time. If you would like to visit the White Lion, then we will be arranging a series of dates for walkthroughs.

## Insurance

The Design Team will hold Professional Indemnity cover set at £2M, Public Liability at

£5M and Employer’s Liability at £10M. If there are any exceptions to this within the subconsultant team, please highlight this in your submission.

## Interview date

The PPC may hold clarification meetings. These will comprise of a 20-minute presentation from the tenderer followed by a 20 minute question and answer session based on the tenderer’s submission. The date of the interviews is TBC.

## Tender submissions – please read carefully

The purpose of the tender response is to enable the PPC to evaluate your understanding of our requirements, the suitability of your proposed approach and experience and skills of your team. Your response should consist of the following:

A written response to the evaluation criteria below.

- Ensure your responses relate to the project brief. Do not include generic information. Any general marketing material about your company or additional appendices that have not been requested will not be considered.

A priced offer in the format request.

- It is the Tenderer’s responsibility to ensure all fees, rates and prices quoted are correct. Tenderers will be required to hold these or withdraw their tender in the event of errors being identified after the submission of tenders.

- If a Tenderer fails to provide fully for the requirements of the specification in the tender it must either absorb the costs of meeting the full requirements of the specification within its tendered price, or withdraw the tender.

- No tender will be considered which is late, for whatever reason nor will changes be permitted after the closing date.

- All tenderers shall keep their respective Forms of Tender valid and open for acceptance by the PPC for 90 days from receipt.

Signatures of appropriately authorised individuals e.g. where the tender is a Limited Company, by a Director; where it is a Partnership, by two authorised partners or by an individual if they are a sole trader. Signatures can be scanned.

Evidence of appropriate insurances. All consultants should have Public and Professional Liability and Companies Employer’s Liability if they have employees.

# Assessment Criteria

Bids will be assessed on the following basis:

Quality – 60%

Cost – 40%

The Client will select a shortlist from the applicants to be invited for interview.  In drawing up the shortlist and making the appointment the following evaluation and scoring process will be used:

●	Relevant design team experience (preferably) from two similar projects that have been completed within the last 3 years. Both should have been funded by the National Lottery Heritage Fund and one a listed building (20%)

●	Qualifications and experience of the proposed team including CVs. No CV must be more than four sides of A4 (20%)

●	Your approach/ methodology for the delivery of the project (20%)

●	Price (40%)

In addition, the following documentation will be required as part of the tender submission:

•	CVs and contact details off each member of the team to be assigned to undertake the role, including a short summary demonstrating their suitability, qualifications and experience

•	Details of three technical referees for work of a similar nature

•	Evidence of public, employers and professional indemnity insurance.

Quality Scoring (60%)

Tenders will be evaluated according to the following four criteria:

- Relevant project management experience (preferably) from two similar projects that have been completed within the last 3 years. Both should have been funded by the National Lottery Heritage Fund and one a listed building (30%)

- Qualifications and experience of the proposed team including CVs. No CV must be more than four sides of A4 (30%)

- Approach to the consultancy including details of communication with the Project Working Group (An advisory board) and CIC/PPC (client) (20%)

- Price (20%)

The PPC will assess Tenderers’ responses according to these criteria and will award points up to the maximum shown against each heading in the Quality evaluation assessment table below. Failure to achieve a rating of satisfactory (i.e. a minimum unweighted score of 3 or above) in any one or more categories may result in the bid being disqualified at the PPC’s discretion.

| Assessment Criteria | Score |
| --- | --- |
| Unacceptable: either no answer is provided, or the answer fails to demonstrate that any of the PPC’s key requirements in the area being measured will be delivered. | 0 |
| Poor: fails to demonstrate how the PPC’s basic requirements in the area being measured will be addressed, giving rise to serious concerns that acceptable outcomes would not be delivered against the project brief. | 1 |
| Weak: barely demonstrates how the PPC’s basic requirements in the area being measured will be addressed, giving rise to concerns whether acceptable outcomes would be delivered against the project brief. | 2 |
| Satisfactory: demonstrates how the PPC’s basic requirements in the area being measured will be addressed so as to deliver acceptable outcomes against the project brief. | 3 |
| Good: demonstrates how most of the PPC’s requirements in the area being measured will be addressed so as to deliver good outcomes against the project brief. | 4 |
| Excellent: demonstrates clearly how all of the PPC’s requirements in the area being measured will be fully addressed so as to deliver excellent outcomes against the project brief. | 5 |

Cost Scoring (40%)

The tenderer who submits the lowest overall price will receive the full score of 20% available for the financial evaluation. Remaining bids will be awarded a score proportionate to the lowest priced bid according to the following formula:

Score = (lowest bid received/ bid price) x 20

Abnormally low or high bids distort evaluation of tenders and where the PCC feels that a bid falls into one of these categories the tender will be asked to explain or clarify their bid. This includes the discounting of daily rates.

## Preparation of Tender

Tenderers are responsible for obtaining all information necessary for the preparation of their response; and all costs, expenses and liabilities incurred in connection with the preparation and submission of the Tender and attending any interviews will be borne by the Tenderer.

The Tenderer is expected to have carried out all research, investigations and enquiries which can reasonably be carried out and to have satisfied itself as to the nature, extent, and character of the requirements of the Contract (in the context of and as it is described in the Specification), the extent of the materials and equipment which may be required and any other matter which may affect its Form of Tender.

Tenderers may seek clarification on any of the points contained in the tender documents at any time up to midday on Wednesday 4th January 2023.

## Non-consideration of Form of Tender

The PPC reserve the right not to award the contract to the highest scoring, lowest priced or to any tenderer; and reserve also the right to accept any of the same in whole or in part. The PPC may also refrain from considering any Form of Tender if it is not in accordance with the Form and Conditions of Tender, or the Tenderer does not provide all the information required or attempts to make variation or alterations to the Form of Tender, Conditions of Contract or the Specification.

## Tenderer’s Warranties

In submitting a Tender, the Tenderer warrants that:

- It has not done any of the acts in the Non-Consideration of Form or Tender,

- all information provided is true, complete and accurate in all respects including details of previous projects being presented as examples,

- it has full power and authority to enter into the Contract.

- it is of sound financial standing, and

- its partners, directors and employees are not aware of any circumstances that may adversely affect such financial standing in the future.

## Confidentiality

The Form of Tender, the Conditions of Contract, the Specification, and all other documentation or information issued by the PPC relating to the Tender shall be treated by the Tenderer as private and confidential for use only in connection with the Tender and any resulting contract and shall not be disclosed in whole or in part to any third party without the prior written consent of the PPC.

The documents which constitute the project and all copies thereof are and shall remain the property of the PPC (whether or not the PPC shall have charged a fee for the supply of such documents) and must not be copied or reproduced in whole or in part and must be returned to the PPC upon their request.

All information provided by tenderers as part of a tender return will be treated as confidential.

## Freedom of Information

Information in relation to this tender may be made available on demand in accordance with the requirements of the Freedom of Information Act 2000.

Tenderers should state if any information supplied by them is confidential or commercially sensitive or should not be disclosed in response to a request for information under the Act, and should state why they consider the information to be confidential or commercially sensitive.

This will not guarantee that the information will not be disclosed, but will be examined in the list of the exemptions provided in the Act.

## ATTACHMENT 1: Form of Tender

Please complete this form and include it with your responses to the questions above.

## Project: Save The White Lion

Professional Service: Design Team Services

## Name of Tenderer:

I/We, the undersigned, do hereby offer to execute and complete the above mentioned professional services in strict accordance with the Schedule of Services for the following lump sum fee:

£ 	plus VAT for the development phase (RIBA Stage 2/3)

£ 	plus VAT for the delivery phase (RIBA Stage 4 to completion)

Confirm figure in words: 	plus VAT

Resources

Please state the number of days and day rates intended for the delivery and development phases in the table below:

|  |  | Development phase |  | Delivery phase |  |
| --- | --- | --- | --- | --- | --- |
| Team | Day Rate £ |  | No. of days | Day Rate £ | No. of days |
| Director/ Partner |  |  |  |  |  |
| Senior Consultant |  |  |  |  |  |
| Consultant |  |  |  |  |  |
| Other – specify |  |  |  |  |  |

The above day rates will be utilised to negotiate any additional works that may be required if deemed to be beyond the reasonable scope of the works specified. All day rates are to be based on a 7.5 hour day and are to include allowance for disbursement

Expenses and Disbursements

The fee offer is to include all expenses and disbursements (including printing charges).

Offer Period

This tender/ offer is to remain open for a period of 90 days from the date fixed to the return of tenders.

Dated this 	day of 	20

|  | Tenderer to provide responses. Some are pass/ fail |
| --- | --- |
| Name of firm or company |  |
| Postal address |  |
| Registered address (if applicable) |  |
| Company number (if applicable) |  |
| Please indicate if you are: a sole trader, partnership, Public or Private Limited Company or other type of organisation |  |
| Main contact |  |
| Contact telephone number |  |
| Contact email address |  |
| Please indicate your level of Employer’s Liability Insurance, the policy number and expiry date 1 |  |
| Please indicate your level of Public Indemnity Insurance, the policy number and expiry date |  |
| Please indicate your level of Professional Indemnity Insurance, the policy number and expiry date |  |
| Signature of authorised person |  |
| Name of authorised person |  |

1 If you do not have any of these insurances please indicate if you will purchase them if awarded the contract. If they are not applicable e.g. you are not an employer please indicate this.

  - Capacity in which signed

| ATTACHMENT 2 - Timetable for Delivery of the Project - V4 |  |  |
| --- | --- | --- |
| Task | Start Month/YR | End Month / Yr |
| Development Stage milestones |  |  |
| Appoint project manager (PM) | Aug-22 | Sep-22 |
| Tender Project Team (PT) | Dec-22 | Jan-22 |
| Consultant Appointment & Start-Up | Jan-22 | Jan-22 |
| RIBA stage 2 works and sign off | Feb-22 | Jun-23 |
| RIBA 3 | Jul-23 | Sep-23 |
| NLHF round 2 application | Oct-23 | Oct-23 |
| Round 2 approval | Mar-24 | Mar-24 |
| Delivery Stage milestones |  |  |
| Round 2 Permission to Start | Apr-24 | Apr-24 |
| RIBA 4 and main contractor procurement | Jun-24 | Oct-24 |
| Capital works | Nov-24 | Nov-25 |
| Internal fit out | Nov-24 | Dec-25 |
| handover and opening | Dec-25 | Dec-25 |
| Contract defects period | Nov -25 | Nov-27 |

# Attachment 3 – Organisational Structure

Pailton Parish Council

Ultimate Client responsible for receiving and payment of funds

Pailton White Lion Working Group (PWLWG)

Parish Council represented CIC represented

Responsible for; liaison with PM, NLHF, fundraising and communication with Community and stakeholders

Project Team

Project Manager—Lead/Chair PWLWG

Architect QS

Business Consultant